| AIM: To ensure that the Authority has appropriate ways of encouraging, listening to and taking account of community views and aspirations about its services |
| --- |
| ACTION | RESPONSIBLE OFFICER |  | PROJECT (IF APPLICABLE) | PROJECT MANAGER | COMPLETION DATE | BUDGET £ |
| (i) ONGOING - Working with WRAP and adapting nationwide press releases for Merseyside market (ii)ONGOING - Working with WRAP and adapting nationwide media alerts for Merseyside market (iii) ONGOING - Co-ordination with District Councils for issuing Merseyside-wide press releases (iv) ONGOING - Co-ordination with District Councils for issuing Merseyside-wide media alerts (v) Co-ordination of Merseyside-wide media work and activities for Compost Awareness Week (6-12 May) | J LALLY |  | WRAP Home Composting Campaign | S Alexander | 31/12/2007 | Internal resources |
| (i) Formulation of Communications and Public Consultation Plan – COMPLETE (ii) Ongoing project group meetings to assess communications position and keep up to date with the project –including liaison with other partners – DEFRA, NWDA, etc regarding communications, marketing and other issues (iii) Implementation of Plan including: a. Sourcing of venue for public consultation day.- COMPLETE b. Design and production of a leaflet for distribution to 14,000 households – includes copywriting, image research, checking and approval – COMPLETE c. Distribution of leaflet to 14,000 households and other venues – additional consultation and information provision with list of other key and major stakeholders - COMPLETE d. Provision and production of information for briefings etc to senior staff and officers including CE’s and Leaders and other members e. Media release for initial proposal – draft and approval - COMPLETE f. Media release for Public consultation day - COMPLETE g. Media release for planning approval COMPLETE h. Ongoing communications to cover – start on site, progress on building, installation of equipment, opening and processing of first waste etc – this would include media, opening, events and liaison with key partners and District Council etc i.Internal Communications with MWDA staff – briefing notes etc | J LALLY |  | DEFRA New Technologies | A Gilbert | 31/03/08 | £5000 (EXTERNAL FUNDING) |
| AIM: To contribute towards achieving the Authority’s aims and objectives by having good internal communications which ensure that both staff and Members are kept well informed and involved. |
| ACTION | RESPONSIBLE OFFICER |  | PROJECT (IF APPLICABLE) | PROJECT MANAGER | COMPLETION DATE | BUDGET £ |
| (i) Initial consideration by MWDA web group – early 2006 (ii) Initial scope considered and other examples sought- early 2006 (iii) Proposal by MANDO (existing web provider) to provide co-ordinated approach for Intranet/Extranet | J LALLY |  | Intranet /Extranet Development | P Pocock | 31/03/08 | £14,000 |
| (i)Review service (ii)Requirements analysis (iii) Improvement Plan |  |  | Best Value Review of Communications | P Pocock | 31/03/08 | Internal resources |
| AIM: To provide information about the Authority’s work which is up-to-date, accurate, relevant and provided in a way suitable for the people receiving it and, to optimise electronic communications to provide information and services by remote access to all those both locally and globally who wish to access information and services in this way |
| ACTION | RESPONSIBLE OFFICER |  | PROJECT (IF APPLICABLE) | PROJECT MANAGER | COMPLETION DATE | BUDGET £ |
| (i) Initial Communications Plan produced for consideration June 2006 – COMPLETE (ii) Review of plan and key actions with Jeff Sears December 2007 – COMPLETE (iii) Production of revised Plan for 2007 implementation (to be completed) March /April 2007 COMPLETE (iv) Implementation of Communication Plan | C GILL |  | HWRC Permit scheme | J Sears | 31/10/08 | £40,000 |
| (i) Initial timetable to be produced for copywriting and production -including quote process for design and print (ii) Sourcing of images (iii) Agree content and method of copy assembly (iv) Coordinate production of copy and statistics (v) Copywriting of final copy (vi) Sign off and approval process ( internal) (vii) Coordination of design and sign off of document (viii) Coordination of print and delivery (ix) Confirmation of web presence | C GILL |  | Publish Annual Plan and BVPP | P Pocock | 30/06/2007 | £9,000 |
| (i) Review of items needed to be finalized and completed (ii) Copywriting ad images for sections and approved (iii) Design changes commissioned to be completed by end of March 2007 (iv) Plan for further development to be considered by Web Group | J LALLY |  | Website | P Pocock | 31/03/08 | £7,000 |
| AIM: To strengthen the Authority’s image and public awareness of its services through the use of a consistent corporate identity |
| ACTION | RESPONSIBLE OFFICER |  | PROJECT (IF APPLICABLE) | PROJECT MANAGER | COMPLETION DATE | BUDGET £ |
| (i)Christmas and New Year Awareness Campaign (ii)Development of Contractual Education Pack (iii) HWRC Awareness and Performance Marketing Programme |  |  | HWRC Education and Awareness Programme | J Connell | 31/03/08 | £75,000 |
| (i) Actions to deliver Education and Awareness Strategy |  |  | Develop and Implement a JMWMS Education and Awareness Campaign | S Alexander | 31/03/08 | £45,000 |
| AIM: To promote effective media relations and to encourage accurate reporting and coverage of events and issues relating to the Authority, recognising that the media may represent alternative views to those of the Authority |
| ACTION | RESPONSIBLE OFFICER |  | PROJECT (IF APPLICABLE) | PROJECT MANAGER | COMPLETION DATE | BUDGET £ |
| SEFTON MEADOWS (EXISTING) (i) Production of Communication and Public Consultation Plan - COMPLETE (ii) Review of plan with Project Manager/Project Team - COMPLETE (iii) Implementation of plan to include: a. Design and production of a leaflet for distribution to 7,500 households – includes copywriting, image research, checking and approval - COMPLETE b. Distribution of leaflet to 7,500 households and other venues – additional consultation and information provision with list of other key and major stakeholders- COMPLETE c. Provision and production of information for briefings etc to senior staff and officers including CE’s and Leaders and other members d. Media release for initial proposal – draft and approval - COMPLETE e. Media release for planning approval f. Ongoing communications to cover – start on site, progress on building, installation of equipment, opening and processing of first waste etc – this would include media, opening, events and liaison with key partners and District Council etc HOLT LANE (NEW) (i) Formulation of Communications and Public Consultation Plan- COMPLETE (ii) Ongoing project group meetings to assess communications position and keep up to date with the project –including liaison with other partners – LCC , Liverpool 20:20 etc regarding communications, marketing and other issues (iii) Implementation of Plan including: a. Sourcing of venue for public consultation day.- COMPLETE b. Design and production of a leaflet for distribution to 36,000 households – includes copywriting, image research, checking and approval c. Distribution of leaflet to 36,000 households and other venues – additional consultation and information provision with list of other key and major stakeholders d. Provision and production of information for briefings etc to senior staff and officers including CE’s and Leaders and other members e. Media release for initial proposal – draft and approval f. Media release for Public consultation day g. Media release for planning approval h. Ongoing communications to cover – start on site, progress on building, installation of equipment, opening and processing of first waste etc – this would include media, opening, events and liaison with key partners and District Council etc i. Internal Communications with MWDA staff – briefing notes etc j. Extensive consultation, visits etc with local Cllrs (k) Extensive consultation, meetings etc with local businesses | J LALLY C GILL |  | HWRC Programme | L Fairhurst | 31/03/2009 31/03/08 | Complete £5000 |
| (i) Development of list of final communication issues with site (ii) Development of plan for official opening (ii) Input into best practice visits – liaison and planning with MWHL (iii) Ongoing brief to monitor communications in relation to all operational aspects of the site | C GILL |  | Bidston Integrated Waste Management Facility | L Fairhurst | 30/09/2007 | £5000 |
| (i) Formulation of Communications and Public Consultation Plan- COMPLETE (ii) Ongoing project group meetings to assess communications position and keep up to date with the project –including liaison with other partners – LCC , etc regarding communications, marketing and other issues (iii) Implementation of Plan including: a. Sourcing of venue for public consultation day. COMPLETE b. Design and production of a leaflet for distribution to 25,000 households – includes copywriting, image research, checking and approval - COMPLETE c. Distribution of leaflet to 25,000 households and other venues – additional consultation and information provision with list of other key and major stakeholders - COMPLETE d. Provision and production of information for briefings etc to senior staff and officers including CE’s and Leaders and other members - COMPLETE e. Media release for initial proposal – draft and approval - COMPLETE f. Media release for Public consultation day - COMPLETE g. Media release for planning approval- COMPLETE h. Ongoing communications to cover – start on site, progress on building, installation of equipment, opening and processing of first waste etc – this would include media, opening, events and liaison with key partners and District Council etc i. Internal Communications with MWDA staff – briefing notes etc j. Extensive consultation, visits etc with local Cllrs - COMPLETE (k) Attendance and advice given at Public consultation day – COMPLETE | C GILL |  | Gillmoss IVC | L Fairhurst | 31/03/2007 | Completed |
| (i) Formulation of Communications and Pre and Post Public Consultation Plan (ii) Ongoing project group meetings to assess communications position and keep up to date with the project –including liaison with other partners regarding communications, marketing and other issues (iii) Extensive programme of pre application public consultation (iv) Implementation of Plan including: a. Sourcing of venue for public consultation day. b. Design and production of a leaflet for distribution to ****** households – includes copywriting, image research, checking and approval - c. Distribution of leaflet to *households and other venues – additional consultation and information provision with list of other key and major stakeholders - d. Provision and production of information for briefings etc to senior staff and officers including CE’s and Leaders and other members - e. Media release for initial proposal – draft and approval - f. Media release for Public consultation day - g. Media release for planning approval- h. Ongoing communications to cover – start on site, progress on building, installation of equipment, opening and processing of first waste etc – this would include media, opening, events and liaison with key partners and District Council etc i. Internal Communications with MWDA staff – briefing notes etc j. Extensive consultation, visits etc with local Cllrs (k) Attendance and advice given at Public consultation day * No of household will identified | C GILL |  | Second MRF | L Fairhurst | 31/03/08 | £10,000 |
| (i) Development of Site selection and Information Management Protocol (ii) Develop a Communications Master Action Plan to deliver all detailed communications and public consultation for the proposed large and smaller sites estimated at 4-6 large planning applications and up to 10- 12 smaller facilities) – Each of these will require their own tracked communication programme | C GILL |  | Deliver a Planning and Sites Strategy for MWDA | C Stockton | 31/12/2008 | £2.8M (2007-2009) |
| AIM: To continue to improve joint working with District Councils in relation to communications and marketing. |
| ACTION | RESPONSIBLE OFFICER |  | PROJECT (IF APPLICABLE) | PROJECT MANAGER | COMPLETION DATE | BUDGET £ |
| (i) To deliver communications for the Waste Prevention Action Programme | C GILL |  | Develop and Implement the Waste Prevention Programme | S Donaldson | 31/03/2008 | £8000 |
| (i) To deliver communications for Corporate Social Responsibility Policy | C GILL |  | Corporate Social Responsibility Policy | S Donaldson | 31/03/08 | £2000 |
| (i) To deliver communications for Sustainability Policy |  |  | Sustainability Policy | S Donaldson | 31/03/08 | £2000 |
| (i) Brief prepared re: production and presentation of review of Strategy – input into design etc | C GILL |  | Develop the Joint Municipal Waste Management Strategy for Merseyside | S Donaldson | 31/03/2008 | £4000 |
| (i) Initial Communications proposal made to SOWG (ii) SOWG feedback that proposal was acceptable (iii) WRAP Communications workshop 8th March 2007 (iv) Revised proposal and details to go to SOWG April 2007 (v) Formulation of Joint Communications Working Group | C GILL |  | Joint Communications | P Pocock | 31/03/08 (ongoing) | £100,000 |
| (i)Communications for the formal, corporate aspects of the Procurement Project– key milestones and announcements etc in addition support for briefings and presentations and detailed information provision for key stakeholders ( Waste Summit) etc (ii) Communication overview and actions for the WMRC Contracts – to include communication for CD process, development of Confidentiality Protocol, key announcements etc and Bidders Days (iii) Communication overview and actions for the RR Contracts – to include communication for CD process, development of Confidentiality Protocol, key announcements etc and Bidders Days and announcement of PFI funds (iii) Management of key communications around the LAWDC (MWHL) to include announcements, potential media issues etc (iii) Management of key issues such as WRF claim, Hafod and input into MWHL communication day to day operational and other issues as needed etc in relation to procurement (iv) Reactive communications requirements as needed in relation to the procurement process | C GILL |  | To procure waste management services and facilities to meet the requirements of the JMWMS | C Beer | 31/03/08 | £10,000 |

# Text boxes

## COMMUNICATIONS STRATEGY: ACTION PLAN