WASTE PREVENTION ACTION PLAN

| - Activity 1: Joint Communications Information |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Supports Strategy Objective Nos. | Objectives | Actions | - Lead Partner | Main Impacts and Benefits | - Resources | - Delivery Years / Start Quarters |  |  |
|  |  |  |  |  |  | 2011/12 | 2012/13 | 2013/14 |
| 1, 2, 3, 4, 5, 6, 8, 9 | 1. To provide simple and consistent messages on waste prevention across Merseyside and Halton. | 1.1 Develop media outlets as a communication tool (including websites, local press, literature, facebook, twitter) to provide up to date information for residents and stakeholders. | MWDA | Provision of information for effective waste prevention actions by residents and stake-holders | PID MWDA officer time equivalent Advertorial space £30,000 (including design costs). | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 Sponsorship of Its Our World | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 1.2 Establish baseline of hits on partner websites in 2011 relating to Waste Prevention and set future targets. | WAPT | Provision of an understanding of stakeholder activity and understanding and the provision of reporting information | WAPT officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 Baseline | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 1.3 All WAPT Group officers to provide and share relevant information to ensure Partnership web-site is used for maximum exposure of issues identified in Strategy etc.. | WAPT | More effective use of website. Increased access by residents to obtain advice and information on waste prevention | WAPT officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 1.4 Develop and apply common communications media to increase recycling capture rates and reduce contamination of recyclable materials where appropriate. | WAPT District | Common messages to residents to help them increase recycling yields | WAPT officer time equivalent District officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  | 2. Consider through research the potential to establish a Waste Prevention Forum for Merseyside and Halton residents. | 1.5 Develop quarterly /seasonal Waste Prevention newsletter ‘Make a World of Difference’ for residents and stakeholders incorporating information provided by WAPT | MWDA | Engagement with stakeholders to increase participation, good practice and innovation to reduce waste arisings. | Communications Plan MWDA officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 PID | Q3 | Q3 |
|  |  |  |  |  |  | Q4 Implement Jan 2012 | Q4 | Q4 |

| - Activity 2: Love Food Hate Waste Campaign |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Supports Strategy Objective Nos. | Objectives | Actions | - Lead Partner | Main Impacts and Benefits | - Resources | - Delivery Years / Start Quartes |  |  |
|  |  |  |  |  |  | 2011/12 | 2012/13 | 2013/14 |
| 1, 2, 3, 4, 5, 6, 7, 9 | 2. To reduce the amount of food waste within the Liverpool City Region. | 2.1 To continue to deliver the Love Food Hate Waste campaign focusing on high public attendance events across Merseyside and Halton. | MWDA/WAPT | More efficient purchase and use of food and drink. CFWRs = 78 kgs of food waste diverted from landfill = 4,914 tonnes diverted 3,685 CO2e tonnes avoided | MWDA/WAPT officer time Equivalent £26, 000 | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 Evaluate Nov 2011 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 Undertake detailed CFWR survey of database members Develop CFWR Pledge scheme | Q4 | Q4 |
|  |  | 2.2 Develop a LFHW ‘pyramid training’ programme consistent with WRAP. | MWDA | Disseminate tools to promote more efficient use of food | MWDA officer time Equivalent | Q1 Evaluate ‘train the trainer’ June 2011. | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 Identify future delivery mechanism | Q4 | Q4 |
|  |  | 2.3 Identify relevant body/ies to deliver a large scale LFHW campaign across Merseyside and Halton. | MWDA |  | MWDA officer time Equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 See LFHW evaluation in 2.1, Q4 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 2.4 To engage and develop working relationship with retailers and the food and drink industry to support food waste reduction | MWDA/WAPT | More effective use of food across supply chain. Redistribution of surplus food and drink. | MWDA/WAPT officer time Equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 PID | Q4 | Q4 |
|  |  | 2.5 Promote the issue of food waste to Council and public sector employees and businesses across Merseyside and Halton | MWDA/WAPT | More sustainable purchasing and use of food | MWDA/WAPT officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 PID | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |

| - Activity 3: Textiles |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Supports Strategy Objective Nos. | Objectives and Targets | Actions | - Lead Partner | Main Impacts and Benefits | - Resources | - Delivery Years |  |  |
|  |  |  |  |  |  | 2011/12 | 2012/13 | 2013/14 |
| 1, 2, 3, 4, 5, 6, 8, 9 | 3. To encourage the diversion of textiles from the residual bin and encourage recycling, re-use and repair. | 3.1 To review existing textile recycling within Merseyside and Halton area. | MWDA |  | MWDA officer time equivalent | Q1 Review | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 3.2 To explore ways of increasing textile capture linked to recycling credits | MWDA | Increase amounts of textiles being reused or recycled. | MWDA officer time equivalent £16,000 (Envirolink Budget) | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 Develop Project | Q2 | Q2 |
|  |  |  |  |  |  | Q3 Report to Authority | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 3.3 To explore joint working and awareness raising with Universities and students to promote textile recycling and re-use | MWDA/WAPT | More efficient use of clothing and textiles Could work this up as PID relating to Fashion show at Gilmoss next year? | MWDA/WAPT officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |

| - Activity 4: Smart Shopping |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Supports Strategy Objective Nos. | Objectives | Actions | - Lead Partner | Main Impacts and Benefits | - Resources | - Delivery Years / Start Quarters |  |  |
|  |  |  |  |  |  | 2011/12 | 2012/13 | 2013/14 |
| 1, 2, 4, 5, 6, 8, 9 | 4. To promote the concept of smarter shopping with the aim of reducing packaging and food waste | 4.1 Develop relationships with retailers to explore joint working on packaging issues | MWDA | Improve products along supply chain. More effective purchasing by residents | MWDA officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 4.2 Work with Public, private and community sectors and support organisations to promote shared shopping to targeted audiences. | MWDA | Use 2.1 CFWR factors for diversion and carbon savings | MWDA officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 4.3 Continue to work in partnership with community groups and faith groups to encourage smart shopping messages. | MWDA F4C | Use 2.1 CFWR factors for diversion and carbon savings | MWDA officer time equivalent MWDA £5,000 F4C officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 4.4 Develop Zero Waste Areas in partnership with other organisations across the City Region (Wirral Area?) | MWDA | Use 2.1 CFWR factors for diversion and carbon savings | MWDA officer time equivalent Wirral officer time equivalent | Q1 | Q1 PID | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |

| - Activity 5: Composting (Home, Community, Commercial) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Supports Strategy Objective Nos. | Objectives and Targets | Actions | - Lead Partner | Main Impacts and Benefits | - Resources | - Delivery Years / Start Quarters |  |  |
|  |  |  |  |  |  | 2011/12 | 2012/13 | 2013/14 |
| 1, 2, 4, 5, 6, 8, 9 | 5. To promote the benefits of Home, Community and commercial Composting in terms of reduction to landfill and carbon | 5.1 To encourage Merseyside and Halton residents to purchase home compost bins through the National Framework Monitor the number of hits on the National Framework website. | MWDA | Disseminate advice and information to residents to reduce waste arisings Compost bin diversion = 150kgs per annum. Tonnes diverted = 4,745 CO2e prevented = 422 t | MWDA officer time equivalent | Q1 Add appropriate links to partner websites | Q1 Make specific push on sales during Compost Awareness Week 2012 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 Lead article for IOW | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 Re-print WRAP Home Compost booklet (Jan) | Q4 | Q4 |
|  |  | 5.2 Explore the feasibility of establishing a composting support network for Merseyside and Halton residents | WAPT | Disseminate advice, information and support to residents to reduce waste arisings | WAPT officer time equivalent | Q1 | Q1 Potential start | Q1 |
|  |  |  |  |  |  | Q2 Feasibility | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 5.3 Encourage and promote ongoing use of home composting bins through a variety of outlets including media, garden centres etc. | WAPT Wirral | Disseminate advice, information and support to residents to reduce waste arisings | WAPT officer time equivalent Wirral officer time equivalent £3,500 | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 PID | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |

| - Activity 6: Reducing unwanted Junk Mail |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Supports Strategy Objective Nos. | Objectives | Actions | - Lead Partner | Main Impacts and Benefits | - Resources | - Delivery Years / Start Quarters |  |  |
|  |  |  |  |  |  | 2011/12 | 2012/13 | 2013/14 |
| 1, 2, 3, 4, 5, 6, 8, 9 | 6. To encourage and facilitate residents to reduce their levels of unwanted mail. | 6.1 To promote sign up to the Mail Preference Service and Royal Mail’s door-to-door opt-out service across Merseyside | Wirral WAPT | Average Junk Mail = 4kg pp/yr Divert 460 tonnes 437 CO2e tonnes avoided | WAPT officer time equivalent MPS database £300 Card options and costs to be obtained? | Q1 Monitor ‘Sign ups’ | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 Distribute cards | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 6.2 Explore feasibility of working with Estate Agents and other external organisations to encourage residents to reduce junk mail and use redirection of mail services etc. | WAPT |  | WAPT officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 PID | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |

| - Activity 7: Re-use and Repair |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Supports Strategy Objective Nos. | Objectives and Targets | Actions | - Lead Partner | Main Impacts and Benefits | - Resources | - Delivery Years / Start Quarters |  |  |
|  |  |  |  |  |  | 2011/12 | 2012/13 | 2013/14 |
| 1, 2, 3, 4, 5, 6, 8, 9 | 7. Aim to encourage and facilitate greater donation of unwanted goods within the Merseyside and Halton area. 7.1 Aim to encourage and facilitate greater re-use of household items 7.2 Establish baseline to set future targets and increase in number of re-use projects with 3rd Sector. | 7.1 To provide guidance and information to encourage residents to consider re-use schemes when they no longer need household items through a variety of media. | MWDA WAPT | More efficient use of products | TBC | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 7.2 To continue to explore all reasonable opportunities to develop effective partnership working with community re-use organisations, 3rd sector organisations and charitable organisations | MWDA | More efficient use of products | TBC | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 PID | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 7.3 To explore opportunities of working with Universities to promote re-use amongst students. (Linked to 3.3) | WAPT | More efficient use of products | TBC | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 PID | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 7.4 Increase Swap Day activities through the promotion of the Swap Day guidance. | MWDA WAPT |  | MWDA officer time equivalent | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 Review and update | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 7.5 To capture small reusable WEEE at household level across the Liverpool City Region to prevent their disposal to landfill. | MWDA | More efficient use of pro-ducts 1,277 tonnes diverted from landfill per annum | Local Project fund application unsuccessful | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |

| - Activity 8: Research, Development and Training |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Supports Strategy Objective Nos. | Objectives and Targets | Actions | - Lead Partner | Main Impacts and Benefits | - Resources | - Delivery Years / Start Quarters |  |  |
|  |  |  |  |  |  | 2011/12 | 2012/13 | 2013/14 |
| 1, 2, 3, 4, 5, 6, 8, 9 | 8 To ensure activities within the Action Plan are supported by robust research and development into evidence base. | 8.1 Development of Pyramid Training concept for other Waste Prevention projects. | MWDA | Design and dissemination of tools | TBC | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 | Q3 |
|  |  |  |  |  |  | Q4 October 2011 | Q4 | Q4 |
|  |  | 8.2 To explore opportunities to support the third sector and community groups in skills development | MWDA |  | TBC | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 | Q3 PID | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |
|  |  | 8.3 To explore opportunities for working with Universities and colleges to develop research projects for the delivery improvement of sustainable waste and resource management. | MWDA WAPT |  | TBC | Q1 | Q1 | Q1 |
|  |  |  |  |  |  | Q2 | Q2 | Q2 |
|  |  |  |  |  |  | Q3 PID | Q3 | Q3 |
|  |  |  |  |  |  | Q4 | Q4 | Q4 |

KEY

|  | No activity |
| --- | --- |
|  | Activity underway |
|  | Activity pending evaluation |