APPENDIX 1

JMWMS PROGRAMME PLAN – NOVEMBER 2009

| DATES | PROGRAMME MANAGEMENT WORKSTREAM | ENGAGEMENT/ CONSULTATION WORKSTREAM | EVIDENCE/ DATA MONITORING/ EVALUATION WORKSTREAM | WASTE COMPOSITION ANALYSIS WORKSTREAM | SA/SEA WORK STREAM | MERSEYSIDE COLLECTION AUTHORITIES WORK STREAM | HALTON WORK STREAM |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PRE APRIL 2009 | Scoping report ratified by all partner authorities. SOWG work plan and resources ratified MWDA budget agreed. |  |  |  |  |  |  |
| APRIL 2009 | MWDA agrees work programmes against budget and evaluation criteria for tenders |  |  |  |  |  |  |
| MAY 2009 |  |  |  | MWDA prepare and agree output spec. MWDA issue OJEU and PPQs |  |  |  |
| JUNE 2009 | SOWG agree project management and establish steering group. |  |  |  |  |  |  |
| JULY 2009 | Steering group meeting (29.07). Agreed process and programme, risk management. TOR and any additional resource requirements. |  |  | Evaluation of PQQs and call for tenders completed. |  |  |  |
| AUGUST 2009 |  |  | Commence data gathering and analysis including development of a model. [Should be consistent with Procurement, DCAPS, DPD and RSS]. Prepare model. |  |  | Agreement by SOWG and RPIG to update, review and undertake SA’s of DCAP |  |
| SEPT 2009 | Steering group meeting. 22/09/09 Agree TOR and discuss risk management. |  | Develop model and agree further actions at steering group. | Tenders received 9th September, Quality and financial evaluations completed. |  |  |  |
| OCTOBER 2009 |  |  |  | Tender report written. |  |  |  |
| NOV 2009 KEY DATE: RRC DECISION 27TH NOV | Steering Group meeting 4/11/09 Steering group meeting. (need to agree work plan and budgets for 2010/11) |  | Data Group and RPIG to develop and draft monitoring and evaluation strategy prior to workshops | Agree award and issue tender. Hold inception meeting with consultants. |  | Complete updates on DCAPS. |  |
| DEC 2009 | Steering Group meeting 2/12/09 Baseline Information Development of baseline report – where we are today.(using new model) Consider partnership and governance options. Agree what final JMWMS document should be. | Develop output spec for engagement, communication and consultation tenders Call for tenders. | Appoint consultant to prepare issues and options paper and organise workshop. (This work may include the life cycle analysis or done with SA/SEA? |  | MWDA to prepare and agree output spec for SEA/SA tender and call for tenders (involve districts). |  |  |
| JANUARY 2010 | Steering Group meeting 13/1 Issues and Options Agree output spec and process for evaluation of options. SEA/SA Agree SEA options and criteria Gap analysis [Evaluation should consider contribution made by each tier of hierarchy in turn starting with waste prevention] Budget report to MWDA by 4th Jan for 5th February Authority meeting. | Evaluate tenders Appoint consultant to develop engagement/consultation strategies. |  | Winter analysis begins | Evaluate tenders Appoint consultants Develop options and assessment criteria. [Consistent if not the same as the evaluation of options for strategy] |  |  |
| FEBRUARY 2010 Milestone – referral to Members on Issues and Options as part of wider consultation | Steering Group meeting 24/2? Wider consultation on issues and options alongside SEA consultation (5 weeks?) [Consistent with SEA requirements and if possible how SEA of DPD was undertaken]. | Draft strategies produced. (Stakeholder group with Veolia to be established) | SOWG facilitated issues and options workshop |  | Develop scoping report and send to statutory consultees and others 5 week consultation to be completed by mid-March at latest. | Action Planning workshops to agree initiatives and responsibilities. |  |
| MARCH 2010 |  | Engagement, communications and consultation strategies produced and agreed by steering group. | Options evaluated and report produced |  | Draft Environmental Report setting out preferred option including action plans for each area of hierarchy. |  |  |
| APRIL 2010 | Steering Group Meeting 7/4? SOWG agree final issues and options report. Headline Strategy Develop draft Headline Strategy and policies Costs/Performance against criteria for hierarchy | Develop output spec for tenders for engagement, communications and consultation implementation. Call for tenders |  | Spring analysis begins | Commence SAs of DCAPS | Commence full reviews of District Council Action Plans (DCAPS) |  |
| MAY 2010 | Steering Group Meeting 19/5 | Purdah period for engagement and comms |  |  |  |  |  |
| JUNE 2010 | Steering Group Meeting 30/6 Action Planning Workshops to agree initiatives, responsibilities Iteration with respect to initiatives | Evaluate tenders and award contract for implementation. Award tenders | Action Planning workshops to agree monitoring protocols, indicators and mitigation measures. |  |  |  |  |
| JULY 2010 Milestone referral back to members in advance of public consultation |  |  | Finalise monitoring and evaluation action plan to include in draft strategy. |  |  |  |  |
| AUGUST 2010 | Steering Group meeting 11/8 Revise Headline Strategy |  |  | 2 August Final Analysis report submitted and data feed into strategy. |  |  |  |
| SEPTEMBER 2010 | Steering Group meeting | Commence public consultation (12 weeks) |  |  |  |  |  |
| OCTOBER 2010 | Steering Group meeting |  |  |  | Complete SAs of DCAPS | Complete reviews of DCAPS |  |
| NOVEMBER 2010 | Steering Group meeting | End of public consultation |  |  |  |  |  |
| DECEMBER 2010 | Steering Group meeting |  |  |  | (Final SA Report on Headline strategy?) |  |  |
| JANUARY 2011 | Steering Group Meeting 12/1 Finalise Action Plans with Implementation Timetable | Receipt of consultation report and how consultees views a reflected in proposed options (six weeks after end of consultation) |  |  |  |  |  |
| FEBRUARY 2011 Milestone referral back to members on public consultation | Steering Group Meeting |  |  |  |  |  |  |
| MARCH 2011 | Steering Group Meeting Earliest date to draft final Headline Strategy |  |  |  |  |  |  |
| APRIL 2011 | Steering Group Meeting |  |  |  |  |  |  |
| MAY 2011 | Steering Group Meeting | Local Elections |  |  |  |  |  |
| JUNE 2011 | Steering Group Meeting Sign off of final draft Strategy before ratification |  |  |  |  |  |  |
| JULY 2011 Milestone referral back to members prior to formal ratification. | Commence ratification process |  |  |  |  |  |  |
| AUGUST 2011 |  |  |  |  |  |  |  |
| SEPTEMBER 2011 |  |  |  |  |  |  |  |
| OCTOBER 2011 | End of ratification process |  |  |  |  |  |  |
| NOVEMBER 2011 | Commence design and printing of new strategy. |  |  |  |  |  |  |
| DECEMBER 2011 | Publication of Strategy |  |  |  |  |  |  |